## Sheet1
| Create At |  | Month/Year
No. | Site | S/N | EquipmentName | Category | Status | Nature Of Breakdown | Causes | Start Repair | End Repair | Action | Spare Part | Spare Part S/N | Brand | QTY | Unit | Spare Part Price | Eqipment Cost | SiteCost | Person in Charge | Equipment Stop | Equipment Resume | Duration

## StandBy MCR225A (hidden)
Tower crane Potain MCR225A Luffing
Serial No: | 350251 | Site: | PL
MFD: |  | From: | WDTP
Register date: |  | Start on site: | 2020-08-28
Dismantle: | 2021-09-07 | Last work Hrs:
Election: | 2020-08-26 | Start Work Hrs:
No. | Site | Action Date | Working Hrs | Main part Component | Device name | Control | Cause | Action | Part | Code | Band | QTY | Unit | Cost | Supplier | Man Cost (Baht/Hrs) |  | Operater | Checker | Stop Machine |  | Start Machine |  | All time stop
1 | PARK-24 | 2016-05-09 |  | Mechaical | Election Machine |  | Site need to use machine | Election Tower crane | [11 empty] | 2016-05-09 |  | 2016-05-14
2 | PARK-24 | 2016-08-18 |  | Mechanic | Check cycle Time 3 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each | [5 empty] | Mr.Ronnachai S. | 2016-08-18 |  | 2016-08-18 |  | 3 Hrs
[9 empty] | Grease all machine |  |  | 1 | Each
3 | PARK-24 | 2016-11-12 |  | Mechanic & Electical | Check cycle Time 6 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each | [5 empty] | Mr.Ronnachai S. | 2016-11-12 |  | 2016-11-12 |  | 5 Hrs
[9 empty] | Check Electical system |  |  | 1 | Each
[9 empty] | Grease all machine |  |  | 1 | Each
4 | PARK-24 | 2017-02-05 |  | Mechanic | Check cycle Time 3 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each | [5 empty] | Mr.Ronnachai S. | 2017-02-05 |  |  |  | 3 Hrs
[9 empty] | Grease all machine |  |  | 1 | Each
5 | PARK-24 | 2017-05-11 |  | Mechanic & Electical | Check cycle Time 6 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each | [5 empty] | Mr.Ronnachai S. | 2017-05-11 |  | 2017-05-11 |  | 5 Hrs
[9 empty] | Check Electical system |  |  | 1 | Each
[9 empty] | Grease all machine |  |  | 1 | Each
6 | PARK-24 | 2017-08-10 |  | Mechanic | Check cycle Time 3 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each | [5 empty] | Mr.Ronnachai S. | 2017-08-10 |  | 2017-08-10 |  | 3 Hrs
[9 empty] | Grease all machine |  |  | 1 | Each
7 | PARK-24 | 2017-09-11 |  | Mechaical | Dismantle Machine |  | Site don't want to use machine | Dismantle machine | [11 empty] | 2017-09-11 |  | 2017-09-15
8 | PL | 2017-09-16 |  | Mechanic & Electical | Check status tower crane | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Trolley Gear Oil | SCH 630 | MOBIL | 13 | Liter | [5 empty] | Mr.Siwakorn R. | 2017-09-16 |  | 2017-09-23 |  | 8 Day
[9 empty] | Hoist Gear Oil | SCH 629 | MOBIL | 13 | Liter
[9 empty] | Slewing Gear Oil | Mobiltac 81 | Mobil | 13 | Liter
[9 empty] | Paint Color all machine |  |  | 1 | Each
[9 empty] | Check Electical system |  |  | 1 | Each
[9 empty] | Grease all machine |  |  | 1 | Each
[9 empty] | Calibration Brake |  |  | 1 | Each
9 | NRDD | 2017-09-24 |  | Mechaical | Election Machine |  | Site need to use machine | Election Tower crane | [11 empty] | 2017-09-24 |  | 2017-09-27
10 | NRDD | 2017-12-15 |  | Mechanic | Check cycle Time 3 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each | [5 empty] | Mr.Ronnachai S. | 2017-12-15 |  | 2017-12-15 |  | 3 Hrs
[9 empty] | Grease all machine |  |  | 1 | Each
11 | NRDD | 2018-03-05 |  | Mechanic & Electical | Check cycle Time 6 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each | [5 empty] | Mr.Ronnachai S. | 2018-03-05 |  | 2018-03-05 |  | 5 Hrs
[9 empty] | Check Electical system |  |  | 1 | Each
[9 empty] | Grease all machine |  |  | 1 | Each
12 | NRDD | 2018-06-10 |  | Mechanic | Check cycle Time 3 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each | [5 empty] | Mr.Ronnachai S. | 2018-06-10 |  | 2018-06-10 |  | 3 Hrs
[9 empty] | Grease all machine |  |  | 1 | Each
13 | NRDD | 2018-07-26 |  | Mechaical | Dismantle Machine |  | Site don't want to use machine | Dismantle machine | [11 empty] | 2018-07-26 |  | 2018-07-30
14 | PL | 2018-08-05 |  | Mechanic & Electical | Check status tower crane | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Trolley Gear Oil | SCH 630 | MOBIL | 13 | Liter | [6 empty] | 2018-08-05 |  | 2018-08-20 |  | 15 Day
[9 empty] | Hoist Gear Oil | SCH 629 | MOBIL | 13 | Liter
[9 empty] | Slewing Gear Oil | Mobiltac 81 | Mobil | 13 | Liter
[9 empty] | Paint Color all machine |  |  | 1 | Each
[9 empty] | Check Electical system |  |  | 1 | Each
[9 empty] | Grease all machine |  |  | 1 | Each
[9 empty] | Calibration Brake |  |  | 1 | Each
15 | ESSE-36 | 2018-09-02 |  | Mechaical | Election Machine |  | Site need to use machine | Election Tower crane | [11 empty] | 2018-09-02 |  | 2018-09-06
16 | ESSE-36 | 2018-12-15 |  | Mechanic | Check cycle Time 3 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each |  |  |  |  | Mr.Thitinon D. Mr.Wirat O. | Mr.Ronnachai S. | 2018-12-15 |  | 2018-12-15 |  | 3 Hrs
[9 empty] | Grease all machine |  |  | 1 | Each
17 | ESSE-36 | 2019-03-07 |  | Mechanic & Electical | Check cycle Time 6 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each |  |  |  |  | Mr.Thitinon D. Mr.Wirat O. | Mr.Ronnachai S. | 2019-03-07 |  | 2019-03-07 |  | 5 Hrs
[9 empty] | Check Electical system |  |  | 1 | Each
[9 empty] | Grease all machine |  |  | 1 | Each
18 | ESSE-36 | 2019-06-27 |  | Mechaical | Dismantle Machine |  | Site don't want to use machine | Dismantle machine | [11 empty] | 2019-06-27 |  | 2019-06-30
19 | PL | 2019-07-15 |  | Mechanic & Electical | Check status tower crane | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Trolley Gear Oil | SCH 630 | MOBIL | 13 | Liter | [6 empty] | 2019-07-15 |  | 2019-07-30 |  | 15 Day
[9 empty] | Hoist Gear Oil | SCH 629 | MOBIL | 13 | Liter
[9 empty] | Slewing Gear Oil | Mobiltac 81 | Mobil | 13 | Liter
[9 empty] | Paint Color all machine |  |  | 1 | Each
[9 empty] | Check Electical system |  |  | 1 | Each
[9 empty] | Grease all machine |  |  | 1 | Each
[9 empty] | Calibration Brake |  |  | 1 | Each
20 | UOBH | 2019-08-15 |  | Mechaical | Election Machine |  | Site need to use machine | Election Tower crane | [11 empty] | 2019-08-15 |  | 2019-08-20
21 | UOBH | 2019-11-12 |  | Mechanic | Check cycle Time 3 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each |  |  |  |  | Mr.Thitinon D. Mr.Wirat O. | Mr.Ronnachai S. | 2019-11-12 |  | 2019-11-12 |  | 3 Hrs
[9 empty] | Grease all machine |  |  | 1 | Each
22 | UOBH | 2020-02-05 |  | Mechanic & Electical | Check cycle Time 6 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each |  |  |  |  | Mr.Thitinon D. Mr.Wirat O. | Mr.Ronnachai S. | 2020-02-05 |  | 2020-02-05 |  | 5 Hrs
[9 empty] | Check Electical system |  |  | 1 | Each
[9 empty] | Grease all machine |  |  | 1 | Each
23 | UOBH | 2020-05-17 |  | Mechanic | Check cycle Time 3 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each |  |  |  |  | Mr.Thitinon D. Mr.Wirat O. | Mr.Ronnachai S. | 2020-05-17 |  | 2020-05-17 |  | 3 Hrs
[9 empty] | Grease all machine |  |  | 1 | Each
24 | UOBH | 2020-08-20 |  | Mechaical | Dismantle Machine |  | Site don't want to use machine | Dismantle machine | [9 empty] | Mr.Thitinon D. | Mr.Vittaya M.
25 | PL | 2020-08-21 |  | Mechanic & Electical | Check status tower crane | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Trolley Gear Oil | SCH 630 | MOBIL | 13 | Liter | [6 empty] | 2020-08-21 |  | 2020-08-26 |  | 6 Day
[9 empty] | Hoist Gear Oil | SCH 629 | MOBIL | 13 | Liter
[9 empty] | Slewing Gear Oil | Mobiltac 81 | Mobil | 13 | Liter
[9 empty] | Paint Color all machine |  |  | 1 | Each
[9 empty] | Check Electical system |  |  | 1 | Each
[9 empty] | Grease all machine |  |  | 1 | Each
[9 empty] | Calibration Brake |  |  | 1 | Each
26 | WDTP | 2020-08-26 |  | Mechaical | Election Machine |  | Site need to use machine | Election Tower crane | [9 empty] | Mr.Thitinon D. | Mr.Vittaya M. | 2020-08-26 |  | 2020-08-29
27 | WDTP | 2020-09-29 |  | Electrical | Anti collistion system | Luffing,Swing, | Prevent accidents From a collision of Tower crane | Install anti collistion system | [5 empty] | 10,300 USD |  | 200 | 12 | Mr.Thitinon D. Mr.Apisit O. | Mr.Jirayuth D. Mr.Vittaya M. | 2020-09-29 |  | 2020-09-29 |  | 6 Hrs
28 | WDTP | 2020-11-15 |  | Mechanic | Check cycle Time 3 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each |  |  |  |  | Mr.Thitinon D. Mr.Wirat O. | Mr.Jirayuth D. | 2020-11-15 |  | 2020-11-15 |  | 3 Hrs
[9 empty] | Grease all machine |  |  | 1 | Each
29 | WDTP | 2021-01-11 |  | Electrical | Coil solenoid Luffing | Luffing | Coil burn | Replace Coil solenoid luffing | [5 empty] | 5,727 THB |  |  |  | Mr.Thitinon D. Mr.Apisit O. |  | 2021-01-11 | 8:00 | 2021-01-11 | 14:00 | 6 Hrs
30 | WDTP | 2021-01-12 |  | Electrical | Motor Blower Luffing | Luffing | Blower short circuit | Overhaul motor | [5 empty] | 1926 |  |  |  | Mr.Thitinon D. Mr.Apisit O. |  | 2021-01-12 | 8:00 | 2021-01-12 | 14:00 | 6 Hrs
31 | WDTP | 2021-02-17 |  | Mechanic & Electical | Check cycle Time 6 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each |  |  |  |  | Mr.Thitinon D. Mr.Wirat O. | Mr.Jirayuth D. | 2021-02-17 |  | 2021-02-17 |  | 5 Hrs
[9 empty] | Check Electical system |  |  | 1 | Each
[9 empty] | Grease all machine |  |  | 1 | Each
32 | WDTP | 2021-05-12 |  | Electrical | Connector Motor swing | Swing | Connector cable loose | New tighten | [9 empty] | Mr.Thitinon D. | Mr.Jirayuth D. | 2021-05-12 | 10:00 | 2021-05-12 | 0:00 | 2 Hrs
33 | WDTP | 2021-05-12 |  | Mechanic | Check cycle Time 3 Month | Hook,Luffing,Swing | PM Tower crane | Check and Replace Spare part | Calibration Brake |  |  | 1 | Each |  |  |  |  | Mr.Thitinon D. Mr.Wirat O. | Mr.Jirayuth D. | 2021-05-12 |  | 2021-05-12 |  | 3 Hrs
[9 empty] | Grease all machine |  |  | 1 | Each
34 | WDTP | 2021-08-07 |  | Mechaical | Dismantle Machine |  | Site don't want to use machine | Dismantle machine | [9 empty] | Mr.Thitinon D. | Mr.Vittaya M.